## TRC Project Gantt-Nov 2019
Mississauga Halton LHIN DRAFT TRANSFER OF REHABILITATIVE CARE PILOT (GO LIVE: NOV 18, 2019)
PROJECT GANTT CHART Project Lead: Amy Khan
Participating Sites:
Stroke: Credit Valley Hospital (Unit 1D and Outpatient Seniors Rehab Day Hospital), Mississauga Halton LHIN (Home & Community Care), Closing the Gap, VHA, CBI Health, SE Health,
Lifemark Community Step-Up, Halton Peel Community Aphasia Program
Hip and Knee Bundle Care: Halton Healthcare Oakville site Inpatient Acute/Inpatient Rehab, Outpatient Rehab at OTMH or CPC, SE Health (Home care)
| 2019 | [15 empty] | 2020
Tasks/ Milestones | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Table Top Simulation Stroke
Table Top Simulation H&K Bundle
Post Stroke Simulation changes to TRC form
Final TRC and Patient Form
HSP site champions identification
TRC Pilot Toolkit
TRC Pilot Toolkit distributed to HSP Site Champions
Teleconference with HSP Site champions
Training and Education for front line staff
HSP site: Pilot readiness confirmed
TRC PILOT Begins
Bi-weekly check in with HSP site champions
Mid Project Evaluation
HSP surveys (administered by the LHIN)
Patient Surveys (administered by HSP, excludes hospitals)
HSP survey 2.5 month analysis to support immediate changes
2.5 month HSP survey results analysis shared with HSP site champions and Community Rehab Committee members with identified action items/risks requiring a decision
2.5 month HSP survey result changes (if any) communicated with HSP site champions
Interim project update shared with key project stakeholders
Interim project report shared with GTA Rehab NW
Final project Evaluation
Project end HSP survey (administered by the LHIN)
Patient survey analysis
Manual patient survey collection HSP site champions to send to LHIN
Electroning patient survey analysis by LHIN
Project end HSP and Patieny survey analysis
Regional Implementation Plan & Pilot end Analysis
Recommendations from pilot including Final TRC form and Patient Form
Strategy/approach to onboard all regional sites
Regional Implementation Plan and Pilot end analysis distrbution stakeholders confirmed
Pilot sites notified of project end analysis and changes
Pilot sites to continue using the TRC form with updated pilot end changes
Stroke GO LIVE Nov 18
Administered by HSPs upon patient discharge from rehab program througout the pilot
Hip and Knee Bundle GO LIVE Dec 9